## Slide 2: The “Jermuk” Project
Young Programmers NGO

## Slide 3: What we have so far

## Slide 4: Short Project Description
Youth, Innovation and Community Engagement Project: Series of trainings aiming to develop IT skills among the Youth in Jermuk City.

## Slide 5: Project Summary
In cooperation with two NGOs (Young Programmers NGO and Youth Center of Jermuk) and volunteer experts, this project consists of series of trainings of programming for a group of youngsters in Jermuk City, dedicated to promote academic excellence, community engagement, youth employment and innovation. Within 8 months, 35 youngsters from Jermuk and nearby villages will learn a programming language (Python) with a local volunteer who specializes in the field. At the same time, different professional programmers from Yerevan will travel to Jermuk twice a month to conduct more thorough master classes. At the end of the program, a two-day workshop will be organized with participation of all the beneficiaries as well as the programmers, during which they would split into groups of 2-3 people and would use their knowledge to come up with innovative solutions to tackle issues in the community.

## Slide 6: Project Justification
Jermuk is a small town located in Vayots Dzor Province, the population of which is around 3500 people (800 of which are 14-30 years old). The city is a very important destination for medical tourism, mostly attracting tourists through its surrounding thick forests and mineral water pools. Apart from this, there is high unemployment rate in Jermuk, especially among younger generations, who either move to the capital city Yerevan to pursue their education and start a career, stay in the communities with no further chances for training, or become labor migrants in Russia or Ukraine.

## Slide 7: … (continuation)
There is only one youth-oriented organization in the area, which works towards community development social inclusion, youth programs and other fields for the youth of Jermuk and nearby villages. Currently the center works with around 200 members (12-30 years of age), most of whom do not have vocational training, secondary education or profession. There are no organizations where young people can receive vocational training and learn a profession.
Although this project consists of courses to learn Python (a programming language), this project has a strong focus of combining community engagement and information technology, and tackles issues of the community through innovative ideas.

## Slide 8: Project Goals and Objectives
The paramount goal of this project is to contribute to the development of Jermuk and nearby areas through innovation and inclusion of the youth. Other goals are:
Contribute up-to-date knowledge and skills towards providing betterment to communities and strengthen the sense of belonging among the participants. Provide vocational training in the field of Information Technologies, so that the youth can start a career in programming, become self-sustainable and generate income after the project is over.
Strengthen cooperation between NGO’s in Yerevan, Jermuk and nearby areas.
Create partnership between programmers in Yerevan and Jermuk and nearby areas.
Promote tourism and development through innovation.
Contribute to team-building, equality and democracy.

## Slide 9: Project Description
During 8 months 35 youngsters in Jermuk city will receive free of charge training in Software Engineering at the local youth center by a high-skilled trainer. The center is equipped with up-to-date computers and necessary hardware and software and is ready to welcome new students. Computers are available during working hours of the center for the beneficiaries to practice what they have learnt. The trainer is a young individual, who works in Jermuk and is committed to staying in the community and devote himself to its development.
...

## Slide 10: … (continuation)
The focus of the training would be using innovation and information technologies to promote community engagement and development. Once every two weeks, with the help of “Young Programmers” NGO in Yerevan, high-profile programmers would visit Jermuk and organize full-day workshops to give even more up-to-date knowledge to the participants.
By the end of the project, there will be a 2-day workshop, where the programmers from Yerevan, who previously worked with the students, would return to Jermuk and create distinct projects with them, all oriented towards providing betterment to the community (e.g. creating websites for local B&B’s, creating apps to promote tourism, transportation, etc).

## Slide 11: Impact Amplification Plan
The number of participants is 35, each of which will have the opportunity to start a career in programming in 8 months and generate income with their newly obtained knowledge. That way they can support their families, help local businesses and promote the community.
After the first six months, the center will continue to provide training for both the beneficiaries who want to continue learning, and will welcome new students who want to learn software engineering. Those participants who would want to pass on their knowledge to the future cohorts and help the trainer will be welcome to do so. The center will continue its work with the youth.
Press interviews will be arranged for the program participants and promoted on social media through Social Media sites of the cooperating NGO’s.

## Slide 12: Expected Results and Project Sustainability
Even though this project is only designed for 8 months, the results are expected to be life changing for the participants.
To start off, 35 students will receive training in Software Engineering, which will help them generate income through freelancing and long-distance employment, without having to leave their communities.
During the final workshop/conference, the students will divide into groups and create 10-15 community-oriented projects. Contacts will be established between Jermuk and Yerevan on an institutional level, hopefully providing opportunities for further cooperation. Awareness will be raised on the issues that Jermuk and nearby communities face on daily basis.

## Slide 13: Timetable
Month 1: gathering of potential students, start of the training sessions. First two guest speakers arrive.
Month 2: trainings continue. Second and Third guest speakers organize their trainings.
Month 3-5: Trainings continue.
Month 6: Training sessions are coming to an end. The participants are assigned to think of innovative projects to be able to implement with the trainers.
Month 8: The conference-workshop is held. 12 trainers (number may change), representatives of the NGOs as well as the project manager are in Jermuk.

## Slide 14: Project Staff

## Slide 15: Who does what?
Hakob: Everything
Laura: Grant writing
Lilit:
Alvard: financial part
Sose:
Vahagn: financial part